## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Study startup validation frameworks, multi-agent design patterns, and web search API integration. | Must Have | None | Entire Team | 3- Completed
Sprint 1 | Sprint 1 | US-002 | Design system architecture, agent roles, orchestration flow, and data models. | Must Have | US-001 | Madhusudan Kumar Singh | 3- Completed
Sprint 1 | Sprint 1 | US-003 | Develop startup idea submission interface and structured idea extraction using LLM. | Must Have | US-001 | Madhusudan Kumar Singh | 3- Completed
Sprint 1 | Sprint 1 | US-004 | Integrate Web Search Agent using Tavily API for live market and competitor data retrieval. | Must Have | US-001,US-003 | Siddhant Singh | 3- Completed
Sprint 2 | Sprint 2 | US-005 | Develop Market Opportunity and Customer Segmentation Analysis Agent — evaluates industry size, trends, and target segments. | Must Have | US-004 | Madhusudan Kumar Singh | 3- Completed
Sprint 2 | Sprint 2 | US-006 | Build Competitor Discovery and Comparison Agent — identifies existing players, compares offerings, and highlights gaps. | Must Have | US-004 | Siddhant Singh | 3- Completed
Sprint 2 | Sprint 2 | US-007 | Implement agent orchestration — ensure sequential pipeline execution with context passing between agents. | Must Have | US-004,US-005,US-006 | Entire Team | 3- Completed
Sprint 2 | Sprint 2 | US-008 | Validate market and competitor outputs using sample startup ideas across different domains. | Must Have | US-007 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-009 | Develop SWOT + Risk Analysis Agent. | Must Have | US-007 | Madhusudan Kumar Singh | 3- Completed
Sprint 3 | Sprint 3 | US-010 | Complete remaining agent integration and context passing across the multi-agent workflow. | Must Have | US-005,US-006,US-007,US-009 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-011 | Validate integrated agent outputs and fix agent execution errors. | Must Have | US-010 | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-012 | Test the system using sample startup ideas across different domains. | Must Have | US-011 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-013 | Complete final system integration and bug fixing. | Must Have | US-010,US-011 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-014 | Refine frontend UX and visualization and prepare the deployment. | Must Have | US-013 | Madhusudan Kumar Singh | 3- Completed
Sprint 4 | Sprint 4 | US-015 | Complete Agile documentation, GitHub finalization, and deployment testing. | Must Have | US-013,US-014 | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-016 | Prepare and deliver final live presentation and project demonstration. | Must Have | US-015 | Entire Team | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 36 | 18 | 18 | 13 | 15 | 15 | 7 | 12 | 14 | 10 | 9 | 11 | 4 | 2 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Research startup validation frameworks and methodologies | 01-07-2026 | 07-07-2026 | Entire Team | Research | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-002 | Design system architecture and agent orchestration flow | 01-07-2026 | 07-07-2026 | Madhusudan Kumar | Design | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-003 | Develop frontend UI for startup idea submission | 01-07-2026 | 07-07-2026 | Madhusudan Kumar | Development | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-004 | Integrate Tavily Search API and build Web Search Agent | 01-07-2026 | 07-07-2026 | Siddhant Singh | Development | 3- Completed | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-005 | Test Tavily vs SerpAPI and document comparison | 01-07-2026 | 07-07-2026 | Siddhant Singh | Testing | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-006 | Develop Market Opportunity and Customer Segmentation Agent | 08-07-2026 | 22-07-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-007 | Build Competitor Discovery and Comparison Agent | 08-07-2026 | 22-07-2026 | Siddhant Singh | Development | 3- Completed | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-008 | Implement CrewAI orchestration pipeline | 08-07-2026 | 22-07-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-009 | Migrate from LangGraph to CrewAI | 08-07-2026 | 22-07-2026 | Entire Team | Development | 3- Completed | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-010 | Validate agent outputs with sample startup ideas | 08-07-2026 | 22-07-2026 | Entire Team | Testing | 3- Completed | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-011 | Develop SWOT and Risk Analysis Agent | 23-07-2026 | 05-08-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-012 | Complete MVP MoSCoW Planning Agent | 23-07-2026 | 05-08-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-010 | T-013 | Build Go-To-Market Strategy Agent | 23-07-2026 | 05-08-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-011 | T-014 | Implement quality checks for agent outputs | 23-07-2026 | 05-08-2026 | Siddhant Singh | Testing | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-012 | T-015 | End-to-end testing with multiple startup domains | 23-07-2026 | 05-08-2026 | Entire Team | Testing | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-013 | T-016 | Final system integration and bug fixing | 06-08-2026 | 30-08-2026 | Entire Team | Development | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0
US-014 | T-017 | Refine frontend UI/UX and PDF report generation | 06-08-2026 | 30-08-2026 | Madhusudan Kumar | Development | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
US-015 | T-018 | Finalize GitHub repo structure and documentation | 06-08-2026 | 30-08-2026 | Entire Team | Documentation | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0
US-016 | T-019 | Prepare presentation and project demo | 06-08-2026 | 30-08-2026 | Entire Team | Presentation | 3- Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Team onboarding and project kickoff completed
Sprint 1 | Day 3 | Understanding Tavily API rate limits | Siddhant tested API with free tier and documented limits
Sprint 1 | Day 5 | None | Architecture finalized, Sprint 1 tasks assigned
Sprint 2 | Day 1 | LangGraph orchestration complexity | Decided to migrate to CrewAI for simpler agent management
Sprint 2 | Day 5 | Agent context passing issues | Resolved by standardizing I/O format across agents
Sprint 2 | Day 10 | None | Sprint 2 completed, all agents integrated successfully
Sprint 3 | Day 2 | SWOT agent output inconsistency | Added quality_checks.py to validate agent outputs
Sprint 3 | Day 7 | None | All validation agents working correctly
Sprint 4 | Day 1 | None | Final sprint started, repo cleanup and documentation in progress
Sprint 4 | Day 5 | Agile documentation pending | Siddhant working on agile sheet and README

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 01-07-2026 | 07-07-2026 | Siddhant Singh | Start documenting API comparisons early | Stop spending too much time on setup | Continue researching before coding | Tavily API documented and integrated
2 | Sprint 1 | 01-07-2026 | 07-07-2026 | Madhusudan Kumar | Start creating architecture diagrams | Stop delaying design decisions | Continue team sync meetings | System architecture finalized
3 | Sprint 2 | 08-07-2026 | 22-07-2026 | Siddhant Singh | Start using CrewAI from beginning | Stop using LangGraph for complex flows | Continue daily standups | Migrated to CrewAI successfully
4 | Sprint 2 | 08-07-2026 | 22-07-2026 | Madhusudan Kumar | Start standardizing agent I/O early | Stop building agents in isolation | Continue code reviews | Agent pipeline integrated
5 | Sprint 3 | 23-07-2026 | 05-08-2026 | Siddhant Singh | Start adding quality checks earlier | Stop skipping edge case testing | Continue pair programming | Quality checks implemented
6 | Sprint 3 | 23-07-2026 | 05-08-2026 | Madhusudan Kumar | Start writing tests alongside development | Stop leaving testing to end of sprint | Continue using CrewAI patterns | All agents validated
7 | Sprint 4 | 06-08-2026 | 30-08-2026 | Siddhant Singh | Start documentation earlier | Stop last-minute repo cleanup | Continue systematic code review | Repo and docs finalized